## Sheet1
PE-CE OUTSOURCED REPORT
AS OF: April 24 2024
FOR REGION(S): Region 3
FOR ADMIN ID(S): ODOT, ODOT/LOCAL
Report Contact:PMO
FOR COUNTY(S): ALL
FOR KEY NUMBER(S): ALL
FOR DBE GOAL: All
STIP-FP Data |  | MSP Data | [6 empty] | Programmed STIP-FP Data | [5 empty] | Calculation | MSP Data |  | CRCT
Key # |  | Project Name |  |  | PCS Region | ODOT Lead | Outsourced PE | Outsourced CE | Project Description | Admin By | County | Work Type | PE/PL Programmed Budget | Total Programmed Project Budget | Anticipated RFP Release Time | Kick-off Meeting Date | Bid Let Date | Anticipated DBE Goal
22032 |  | South Myrtle Road: South Myrtle Creek bridge |  |  | Region 3 | DEWALD TERESA L | Yes | Yes | Design to replace the existing bridge with a new bridge that meets current design standards. | ODOT/LOCAL | DOUGLAS | BRIDGE | 413000 | 2528000 | 3rd QTR, 2023 | 2024-02-16 17:00 | 2026-07-30 17:00 | 0.00%
22639 |  | Days Creek Rd: Days Creek Bridge |  |  | Region 3 | DEWALD TERESA L | Yes | Yes | Replace the bridge to restore load rating and access for all vehicles. | ODOT/LOCAL | DOUGLAS | BRIDGE | 684000 | 4096400 | 4th QTR, 2023 | 2024-03-05 17:00 | 2026-03-26 17:00 | 3.00%
22655 |  | Newton Creek Bridge |  |  | Region 3 | DEWALD TERESA L | Yes | Yes | Replace bridge to restore load rating and access for all vehicles. | ODOT/LOCAL | DOUGLAS | BRIDGE | 645800 | 3292100 | 4th QTR, 2023 | 2024-03-22 17:00 | 2026-08-11 17:00 | 0.00%
22663 |  | Trail Creek, County Rd 776 |  |  | Region 3 | OBERLANDER ELI | Yes | Yes | Replace bridge to serve two lanes of traffic. | ODOT/LOCAL | JACKSON | BRIDGE | 585100 | 2978000 | 2nd QTR, 2024 | 2024-08-20 17:00 | 2027-06-18 17:00 | TBD
22914 |  | Garden Valley Rd at Melrose Rd Roundabout |  |  | Region 3 | DEWALD TERESA L | Yes | Yes | Construct a partial multi-lane roundabout at the Garden Valley Road and Melrose Road Intersection to reduce the number and severity of intersection crashes. | ODOT/LOCAL | DOUGLAS | SAFETY | 1891578 | 9014728 | 1st QTR, 2024 | 2024-07-25 17:00 | 2026-07-09 17:00 | TBD
23160 |  | Bilger Creek, County Rd 15 bridge |  |  | Region 3 | DEWALD TERESA L | Yes | Yes | Replace the existing bridge to meet current standards. | ODOT/LOCAL | DOUGLAS | BRIDGE | 430300 | 2122200 | 3rd QTR, 2024 | 2025-01-16 17:00 | 2026-05-28 17:00 | TBD
23427 |  | Libby Lane Paving (Coos County) |  |  | Region 3 | DEWALD TERESA L | Yes | Yes | Repave the road to create a smoother driving surface and extent its useful life. | ODOT/LOCAL | COOS | PRESRV | 182400 | 742400 | 3rd QTR, 2023 | 2024-01-26 17:00 | 2024-06-13 17:00 | 0.00%
Report Total: 7

## Sheet2
About this report Report name: PE-CE Outsourced Report Purpose: To provide forecasted outsourced work to industry partners. This report is posted to the external ODOT Procurement website weekly. Definitions and filters: Filter(s): Projects show on this report according to the following: PE & CE or just PE outsourced: Project will be on the report for 12 months before the PDT kick off date until 3 months after the PDT kick off date. Just CE outsourced: Project will be on the report for 9 months before the bid let date until 1 month after the bid let date. Anticipated RFP Release Time calculation: PE & CE or just PE Outsourced: PDT Kick off - 140 days Just CE outsourced: PS&E Submittal date - 180 days Data sources: RMS, STIP, CivilRights