Chapter 22

Contents

22 Construction Support	22-1

22.1 Authority over the Contract Work	22-1

22.2 Addenda	22-2

22.3 Pre-Construction Conference	22-2

22.4 Material Submittals and Shop Drawing Review	22-3

22.4.1	Pole and Foundation Submittals	22-3

22.4.2	Blue Sheets and Green Sheets	22-4

22.4.1	Field Verification Forms (For Signal Poles and Signal Pole Foundations)	22-4

22.5 Cabinet Print	22-5

22.6 Requests for Information	22-5

22.7 Contract Change Orders	22-7

22.8 Certified Traffic Signal Inspection Certification	22-8

22.9 Construction Issues	22-9

22.9.1	Detection	22-9

22.9.2	Conduits	22-11

22.9.3	Utility Conflicts	22-12

22.9.4	Poles & Foundations	22-13

22.9.5	Unique Situations	22-14

22.9.6	Temporary Signals	22-14

22.9.7	Signs	22-14

22.9.8	Pushbuttons	22-15

22.9.9	Wiring	22-15

22.9.10	Service Cabinet	22-16

22.9.11	Junction Boxes	22-16

# Construction Support

Once the project has been let, the signal designer will provide assistance to the office administering the contract during the advertisement and construction phases. This typically consists of:

- Handing off electronic design files to the construction office for their use & verification

- Clarifying/interpreting information shown in the plans and specifications

- Adding, modifying or deleting information in the plans and specifications as necessary

- Providing a cost estimate for your expected amount of construction support

- Reviewing submittals

- Attending meetings as requested

Construction support should be the highest priority for the signal designer.

Periodic inspection of work as requested

## Authority over the Contract Work

The engineer as defined by the contract documents (project manager/resident engineer) has authority of the contract work. Always work directly with the project manager’s office when providing construction support. DO NOT WORK DIRECTLY WITH THE BIDDER OR CONTRACTOR!

Once the project is let (during the advertisement phase and the construction phase) the engineer has full authority over the work contained in the contract documents. The engineer is defined in the specifications as the chief engineer of the agency acting directly or through authorized representative (section 00110.20). The specifications also define the project manager as the engineer’s representative who directly supervises the engineering and administration of a contract (section 00110.20) and the states the duties and authorities of the project manager (section 00150.01). One of the duties of the project manager is to address any clarification, interpretation, corrections, etc. of the contract documents. This is to ensure that clear, concise information/direction is given to the bidders or the contractor. Contract clarification or interpretation obtained from persons other than the project manager (e.g., the signal designer) are not binding on the agency and unnecessarily complicate administration of the contract.

## Addenda

Changes or corrections to the plans, special provisions or bid items may be required during the advertisement phase. These changes are made by addenda.

If the addendum includes modifying a plan sheet, the plan sheet will need to follow the “revised plans” process described in chapter 21. Revision triangles are required on ALL revised plan sheets as shown in the Contract Plans Development Guide, NO EXCEPTIONS.

In addition, traffic engineering section review and design approval of the revised plan sheet is required as per chapter 2. The TRS dwg. number does not change from the original plan sheet.

## Pre-Construction Conference

After the contract has been awarded and prior to starting work, the contractor must meet with the resident engineer for a pre-construction conference (pre-con). The pre-construction meeting will typically cover the following topics that can impact signal design:

- Utility relocation and potential conflicts

- Identifying known problem areas, identifying procedures to resolve those problems, and establishing a process to resolve future problems in a timely manner

- Calling attention to unique design requirements in the plans and specs

- Project schedule

- Temporary traffic control and staging

- Identification of key personnel and channels of communication

The signal designer should attend the pre-con conference if possible, especially if there are known problem areas, unique design requirements, and/or the contractor or inspector have limited traffic signal construction experience. Obtaining a copy of the agenda can maximize your efficiency as it is not necessary to stay for the entire pre-con, which can be lengthy and cover a wide array of contract topics.

## Material Submittals and Shop Drawing Review

The signal designer may receive different types of submittals to review, but the three main required construction submittals are pole drawings, blue & green sheets, and field verification forms.

### Pole and Foundation Submittals

The signal designer should review these features when receiving pole submittals:

- Are the shop drawing(s) prequalified or not? Verify the shop drawing manufacturer and drawing number(s) with the prequalified list that is in the special provisions 00962.05(a). If the shop drawings are prequalified, no additional structural review is necessary. If the shop drawings are NOT prequalified, contact the region bridge unit for review of the structural aspects.

- The information in shop drawing matches the information in the plans/pole entrance chart:

  - Pole type

  - Mast arm length

  - Mast arm orientation

  - Luminaire arm length

  - Luminaire arm height

  - Luminaire arm orientation

  - Hand hole orientation

  - RTC orientation

  - Loading on the mast arm & pole

  - Any other appurtenances that are specified on the plans (e.g., ornamental base shoes).

After reviewing the submittals, mark them as REVIEWED including your signature and the date. Submit the back to the construction office.

### Blue Sheets and Green Sheets

The traffic engineering section maintains two lists of materials and equipment that show a list of prequalified equipment for use on signal projects. These lists are commonly referred to as the blue and green sheets. They are updated frequently and posted on the traffic signal standards website (click on “product evaluation and approval”).

The blue sheets contain a list of items that are normally qualified by the project manager’s office according to the Non-Field Tested Materials Guide.

The green sheets contain a list of items that are normally accepted for environmental and functional testing by the traffic system services unit (TSSU). This is typically the controller cabinet and equipment contained within.

The contractor is responsible for downloading, appropriately filling out, and submitting copies of the blue and green sheets to the project manager prior to starting work. The second page of the blue and green sheets contains detailed instructions for how to use and process each document.

Always read and follow the instructions on the blue and green sheets.

Typically, the signal designer is not involved in reviewing, using, processing, or approving the green and blue sheets. However, you may be asked to help the inspector review them, usually to make sure that the contractor has included all of the necessary components as required by the plans and specifications. If this occurs, read through and follow the instructions listed on the second page of the submittal.

### Field Verification Forms (For Signal Poles and Signal Pole Foundations)

There are two field verification forms, one for signal poles and one for signal pole foundations. These two forms are required for each large pole on the project (not required for pedestals). Both forms contain information that is intended to verify the exact location of the pole foundation, the vertical clearance for all equipment mounted on the mast arm will meet the 18’ min. to 19’ max., and the anchor rod projection is installed per specification. The forms as well as additional information about their use (flow chart and roles & responsibilities) are on the traffic structures website (click “signal supports, field verification forms”).

These forms are filled out by the project manager’s office prior to installation of the signal pole foundations based on the information provided in the signal plan sheets and design files. However, the signal designer may be asked to help fill them out or review the content.

## Cabinet Print

Per the 00990.70 specification, the cabinet print is provided to the contractor via the project manager’s office during the construction phase. This should occur near the pre-construction conference project milestone, prior to the signal being constructed. See chapter 20 for more information on the process for completing the cabinet print.

## Requests for Information

The project manager’s office will contact the engineer of record when there is a need for interpretation of the plans or the specifications. As mentioned in section 22.1, all requests for information should come from the project manager’s office. If a request from someone other than the project manager office is received, do NOT answer any project specific questions and direct them to the project manager’s office for proper processing of the issue. This may seem overly bureaucratic and unhelpful, but the importance of this process cannot be understated; it is vital that agency communication is directed through a single official source to avoid conflicting, confusing, or inappropriate release of information that may result in time delays, unnecessary expense, or construction claims.

The construction lead will submit any contractor questions, contractor proposals, errors in the plans/specifications, etc. to the engineer of record for review and comment. The engineer of record will determine a proper response back according to the following:

- If clarification of the plans is all that is needed, the engineer of record will provide this information to the project manager with no further action needed from the EOR.

- If a minor change to plans and/or specifications is needed, the engineer of record will submit a proposed solution to region traffic and the region electricians for review and approval. A minor change would be anything that falls under current standard practice. The EOR will give the approved solution to the construction lead (see section 22.7) who will then direct the contractor.

The engineer of record is responsible for providing a solution to issues that arise during construction. The construction lead is responsible for making sure that solution is carried out.

If a major change to plans and/or specifications is needed, the engineer of record will submit a proposed solution to the traffic engineering section, region traffic and the region electricians for review and approval. A major change would involve any deviation from standards. The EOR will give the approved solution to the construction lead (see section 22.7) who will then direct the contractor.

The following flow chart, Figure 22-1, outlines this basic process for handling requests for information and resolving issues during construction.

Figure 22-1 | Changes During Construction Flow Chart

Engineer of record:

This is the person or firm that produced the traffic signal plans. This could be ODOT, local agencies, consultants, etc.

Request for info or changes

Approved solution*

Construction lead:

This is the ODOT designated construction lead. This could be a consultant project manager (CPM), project leader, district permits, local agency liaison, project manager, etc.

ODOT region traffic:

This is the region traffic engineer or the region signal operations engineer

ODOT electricians:

This is the lead electrician for the specific region

Traffic engineering section

Submit proposed solution for comments

MAJOR   CHANGE    ONLY

Submit proposed solution for approval

*Minor changes: Approved solution shall have approval from region traffic and electricians.

*Major changes: Approved solution shall have approval from traffic engineering section, region traffic and electricians.

It’s the engineer of record’s responsibility to ensure all required parties have the opportunity to comment and approve of the approved solution that will be given to the construction lead.

Feedback or approval of proposed solution

Feedback or approval of proposed solution

## Contract Change Orders

Changes or corrections to the plans, special provisions or bid items may be required during the construction phase. These changes are made by contract change orders (CCO).

If a CCO includes modification to a plan sheet, there are two options for resolution:

- Provide written or verbal direction to the project manager of the required change. This change will then be documented in the CCO paperwork and on the plan sheet as-built when the project is completed. If the change is major or includes a deviation from standards, verbal or written approval (such as e-mail) is required by the traffic engineering section.

CCO plan sheet revisions are given the highest priority for traffic engineering section review.

Verbal approval by the traffic engineering section for changes that deviate from standard is acceptable for moving forward during construction.

Produce a revised sealed plan sheet for inclusion into the CCO (see chapter 21 for the revised plans process). This option is recommended if the revision is complex enough that written or verbal directions to the construction lead would be insufficient to properly understand and implement the change. Revision triangles are required on ALL revised plan sheets as shown in the Contract Plans Development Guide, NO EXCEPTIONS. The revised plan sheet does NOT need to be submitted to the traffic- roadway section for review and design approval if the proposed change is minor and doesn’t deviate from standards (e.g., adjustment or deletion of an optional lane use sign). If the change is major (e.g., deviates from the requirements stated in the operational approval) or involves a deviation from standards, the revised plan sheet shall be submitted to the traffic engineering section for review and design approval as per chapter 2. The TRS dwg. number does not change from the original plan sheet.

## Certified Traffic Signal Inspection Certification

The traffic engineering section provides training and certification each year for inspection of ODOT traffic signal installations. While this training is specific to inspection and NOT a requirement for signal designers, it is highly recommended as it will give a better understanding of the materials and construction process related to traffic signals. Class topics include:

- Material qualifications (blue and green sheets)

- Review of the current Inspector’s Manual for Signal Construction

- Exposure to basic signal design

- Standard drawings

- Reading of plans and specifications

The training is taught in two different formats; a 2-day full class and a 1-day re-certification class for those that are more familiar with the subject topics and just need a refresher course highlighting the recent changes. A self-paced virtual training is also available for both formats. An exam is given at the end of each class and certification is given to those that pass. Certification is good for three years.

For more information on these classes, access to the current version of the Inspector’s Manual for Signal Construction, and to register for up-coming classes, visit the ODOT Inspector Certification Program website.

## Construction Issues

This section takes excerpts from actual construction change orders and project manager narratives, grouped into basic categories. See Figure 22-2 through Figure 22-24. Some of these issues could have been resolved prior to construction during the design phase by a site visit to the field to verify conditions or by coordinating with other disciplines. Some result from ambiguity, incomplete, or conflicting information in the contract documents. Others are the result of unexpected conditions that were uncovered during the construction process and would have been hard to predict ahead of time. While not all contract change orders can be avoided, the goal is to minimize the number of CCOs needed to build the contract by producing complete, concise, and field verified contract plans.

It is always more cost effective for the contractor to bid and build what’s shown in the original contract documents than to issue a change order during construction for the same work.

The traffic engineering section reviews contract change order and project manager narratives as they are posted on the ODOT server.

### Detection

Figure 22-2 | CCO – Detection, April 2013

Figure 22-3 | CCO – Detection, November 2012

Figure 22-4 | CCO – Detection, Extra Work Order, August 2012

Figure 22-5 | CCO – Detection, PM Narrative May 2012

### Conduits

Figure 22-6 | CCO – Conduits, January 2013

Figure 22-7 | CCO – Conduits, May 2012

Figure 22-8 | CCO – Conduits, October 2011

### Utility Conflicts

Figure 22-9 | CCO – Utility Conflicts, February 2013

Figure 22-10 | CCO – Utility Conflicts, PM Narrative, September 2012

Figure 22-11 | CCO – Utility Conflicts, Extra Work Order, July 2012

Figure 22-12 | CCO – Utility Conflicts, Force Order, April 2012

### Poles & Foundations

Figure 22-13 | CCO – Poles & Foundations, PM Narrative, October 2012

Figure 22-14 | CCO – Poles & Foundations, August 2012

Figure 22-15 | CCO – Poles & Foundations, PM Narrative, November 2012

### Unique Situations

Figure 22-16 | CCO – Unique Situations, Historic Bridge Issue, October 2012

### Temporary Signals

Figure 22-17 | CCO – Temporary Signals, February 2013

### Signs

Figure 22-18 | CCO – Signs, December 2012

Figure 22-19 | CCO – Signs, April 2013

### Pushbuttons

Figure 22-20 | CCO – Pushbuttons, October 2012

### Wiring

Figure 22-21 | CCO – Wiring, PM Narrative, June 2012

Figure 22-22 | CCO – Wiring, August 2012

### Service Cabinet

Figure 22-23 | CCO – Service Cabinet, May 2012

### Junction Boxes

Figure 22-24 | CCO – Junction Boxes, September 2011